## Slide 1
Task Order | Activities | Study Status (IRB status)
TO #8: MDR-TB Genotyping | Patient interviews, case data abstraction, collection of lab and surveillance data | Data acquisition completed. Analysis ongoing.
NIH: TO #8 Effect of Drug Resistance on Transmissibility and Pathogenicity | RVCT and CI data abstraction on drug resistant cases. | Start-up (Local IRB review pending in L.A.)
TO #21: Acquired Rifamycin-Resistance | NTSS based analysis. Medical record abstraction. | Start-up (IRB approved). Teleconference March 3rd with CDC.
TO #25: TB Mortality | Determine incidence of TB-related deaths. Determine predictors of TB related deaths. | Ongoing. Dr Singh reviewing abstracted data and assigning TB relatedness along with State physicians.
TO #28: MDR Cost 2005-2007 | Hospital and clinic chart reviews. | Ongoing-PH Clinic chart reviews completed. Hospital reviews pending.
TO #29:ImprovingTB/LTBI Screening at HRSA clinics | Assessment of implementation of TB policies and practices. | Meeting with CDC, State and OAPP upcoming.
TBESC Research: CDPH-L.A. TBC
Notes: Pending your decision to participate or not

## Slide 2: Internal Research Activities Data Analysis 2010 -- 2011
Title | Staff | Description | Comments
“Homeless Cluster” | Shameer Poonja, PHA; Giuli Zheng, Ph.D (intern—UCLA MPH); Dr. Singh | Data abstraction and analysis using medical records and genotypic data to: 1) Evaluate ongoing practices; 2) Identify targeted interventions, and 3) Build community partnerships. | Data shared with CHS at First Friday TB Conference on 12/03/10. State TBCB presented info re: genotyping. Ongoing.
“B-Notification Data Analysis” | Shameer Poonja; Ting-Chang Sheu (intern– Pre-Med) | SAS data analysis of B-Notification data: 1) For review by TBC and CHS in order to improve timely and complete evaluation of immigrants. | Preliminary results shared internally January, 2011. Analysis ongoing.
“School Mandate: Acquired Risk of Infection” | Yuwen Yue, Epidemiology Analyst; Dr. Singh | What is the value of our vast store of School Mandate data? 1) How do we interpret acquired risk of infection calculated from this data? 2) Can we estimate baseline LTBI rates in LAC? 3) What does the data tell us about transmission of TB in LAC? | Dr. Lisa Pascopella (State Epidemiologist) will begin collaborating with staff – teleconference 3/03/11.